## Sheet1
Task Name | Start | Finish | Today: | 2017-09-21
RQ1 | 2017-04-01 | 2017-07-14
Be able to model applications based on GUI elements. | 2017-04-01 | 2017-06-30
Extent the input and output alphabet and deal with learning errors. | 2017-07-01 | 2017-07-14
RQ2 | 2017-08-01 | 2017-08-31
Increase time feasibility by adoption of: caching/event-filling/other smart techniques. | 2017-08-01 | 2017-08-31
RQ3 | 2017-09-01 | 2017-09-29
Assess for a set of bugs and vulnerabilities if they can be identified in (enriched) graphs. | 2017-09-01 | 2017-09-07
Formalize algorithms how they can be derived. | 2017-09-08 | 2017-09-29
Validation | 2017-10-01 | 2017-10-30
Correctness | 2017-10-01 | 2017-10-13
Create application that contains the vulnerabilities | 2017-10-01 | 2017-10-06
Assert the tool on vulnerable applications and assess results | 2017-10-08 | 2017-10-13
Metrics | 2017-10-14 | 2017-10-30
Assert the tool on vulnerable applications and assess results | 2017-10-14 | 2017-10-30
Documents | 2017-11-01 | 2017-12-01
Report - Finalization | 2017-11-01 | 2017-11-30
Presentation | 2017-11-19 | 2017-12-01

## Sheet2
Task Name | Elements | Implemented | Written | Status
RQ1
Be able to model applications based on GUI elements. | L* | 100% | 90% | Waiting for review notes
| TTT | 100% | 90% | Waiting for review notes
| Happy Flow | 100% | N/A
| EQ Oracle | 80% | 80% | Read and implement "Moerman J,, 2016, Minimal Separating Sequences for All Pairs of States"
Extent the input and output alphabet and deal with learning errors. | Back + Activities | 100% | N/A
RQ2
Increase time feasibility by adoption of: caching/event-filling/other smart techniques. | Caching | 100% | N/A
| Fast-Forwarding | 100% | N/A
| Happy Flow -> Smart Cache | 75% | N/A
RQ3
Assess for a set of bugs and vulnerabilities if they can be identified in graphs. | Vulnerability presence | N/A | 100% | c:\users\wvanderlee\Work Folders\Documents\Thesis\Literature\Vulnerabilities
Formalize algorithms how they can be derived. | Working implementation | 100% | N/A | Shortcomings of LearnLib and AutomataLib. MealyMachine to Graph. Dijkstra.
| Determine enrichment type | 10% | 0%
| Establish algorithm | 1 of ? | 0%
Validation
Correctness
Create application that contains the vulnerabilities | Might be skipped | 0% | N/A | Requires app dev. Knowledge
Assert the tool on vulnerable applications and assess results | - | 0% | N/A | Requires application selection
Metrics
Assert the tool on (non) vulnerable applications and assess results |  | 0% | N/A | Requires application selection
Documents
Report - Finalization |  | N/A | 0%
Presentation |  | N/A | N/A
Scientific Paper |  | N/A | 0%