## Sheet1
Task Name | Start | Finish
RQ1 | 2017-04-01 | 2017-07-14
Be able to model applications based on GUI elements. | 2017-04-01 | 2017-06-30
Extent the input and output alphabet and deal with learning errors. | 2017-07-01 | 2017-07-14
RQ2 | 2017-08-01 | 2017-08-31
Increase time feasibility by adoption of: caching/event-filling/other smart techniques. | 2017-08-01 | 2017-08-31
RQ3 | 2017-09-01 | 2017-10-25
Assess for a set of bugs and vulnerabilities if they can be identified in (enriched) graphs. | 2017-09-01 | 2017-09-07
Formalize algorithms how they can be derived. | 2017-09-08 | 2017-10-25
| Error States |  | Error tekst on screen / Can't get Toasts
| DeadLocks |  | Leafs in graph
| Improper Platform Usage |  | Activity calling outside graph
| Insecure Communication |  | Problem: Interactive Shell commands to work with i) emulator and ii) mitmproxy
| Insecure Authentication |  | Paths without login state
| Code Tampering |  | Compare to reference model
| Extraneous Functionality |  | Compare to reference model
Validation | 2017-10-01 | 2017-10-30
Assert the tool on vulnerable applications and assess results | 2017-10-14 | 2017-10-30 | Retrieve correctness and metrics
Documents | 2017-10-23 | 2017-12-01
Report | 2017-11-01 | 2017-11-30
0. Abstract
| 1. Introduction |  | 1st revision in construction
| 2. Building Blocks of Model Inference |  | 3rd revision pending feedback Sicco
3. Prior Art on Application Modeling
4. Model Inference Tool
5. Vulnerability Identification on Models
6. Results
7. Discussion and Validation
8. Conclusion and Future Work
Merging Structure/ Layout
Presentation | 2017-11-19 | 2017-12-01
Defense | 12-14-17 | 12-14-17

## Sheet2
Task Name | Elements | Implemented | Written | Status
RQ1
Be able to model applications based on GUI elements. | L* | 100% | 90% | Waiting for review notes
| TTT | 100% | 90% | Waiting for review notes
| Happy Flow | 100% | N/A
| EQ Oracle | 80% | 80% | Read and implement "Moerman J,, 2016, Minimal Separating Sequences for All Pairs of States"
Extent the input and output alphabet and deal with learning errors. | Back + Activities | 100% | N/A
RQ2
Increase time feasibility by adoption of: caching/event-filling/other smart techniques. | Caching | 100% | N/A
| Fast-Forwarding | 100% | N/A
| Happy Flow -> Smart Cache | 75% | N/A
RQ3
Assess for a set of bugs and vulnerabilities if they can be identified in graphs. | Vulnerability presence | N/A | 100% | c:\users\wvanderlee\Work Folders\Documents\Thesis\Literature\Vulnerabilities
Formalize algorithms how they can be derived. | Working implementation | 100% | N/A | Shortcomings of LearnLib and AutomataLib. MealyMachine to Graph. Dijkstra.
| Determine enrichment type | 10% | 0%
| Establish algorithm | 1 of ? | 0%
Validation
Correctness
Create application that contains the vulnerabilities | Might be skipped | 0% | N/A | Requires app dev. Knowledge
Assert the tool on vulnerable applications and assess results | - | 0% | N/A | Requires application selection
Metrics
Assert the tool on (non) vulnerable applications and assess results |  | 0% | N/A | Requires application selection
Documents
Report - Finalization |  | N/A | 0%
Presentation |  | N/A | N/A
Scientific Paper |  | N/A | 0%